{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["公众号H5"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"公众号H5","index":0,"n_rows":66,"n_cols":10,"rows_kept":66,"cut":false,"hidden":false,"merged":[]}
["需求提出人","项目","需求类型","页面","需求内容","解决方案","优先级","需求状态","评审状态","规划版本"]
["林泽阳","公众号用户端","优化","订单支付","确认交易协议","在订单支付页面，支付的按钮上面添加一行选择项，确认交易协议，确认后才点击支付，否则出现toast提示：请先确认交易协议",1,"已完成","已评审"]
["林泽阳","公众号用户端","优化","预约服务","预约服务的页面添加一些超时预约和订单唯一的文字","详看原型",1,"已完成","已评审"]
["林泽阳","运营后台","优化",null,"留言的模块，后台设计有对应接受到订单留言的地方","详看原型",2,"已完成","已评审"]
["林泽阳","运营后台","优化",null,"留言的模块，后台设计有对应接受到预约服务留言的地方","详看原型",1,"已完成","已评审"]
["林泽阳","公众号用户端","优化","发送通知","每个阶段需要发不同的通知","先完成下单和预约成功的短信",1,"已完成","已评审"]
["林泽阳","公众号用户端","优化","首页","促销模块","在BANNER和所有产品之间添加一个促销模块",2,"已完成","已评审"]
["林泽阳","公众号用户端","优化","订单详情","产品售罄功能","可看不可购买，点击购买提示已售罄",2,"已完成","已评审"]
["林泽阳","公众号用户端","优化","订单详情","促销功能展示，需要有限时折扣的显示","添加一个倒计时效果",2,"已完成","已评审"]
["林泽阳","公众号用户端","优化","首页","首页顶部显示LOGO，以及减小宽度","首页顶部显示LOGO，以及减小宽度",0,"已完成","已评审"]
["宗涛张","公众号用户端","优化","首页","苹果端 产品之间没有间隙","增加一点间隙",2,"已完成","已评审"]
["林泽阳","公众号用户端","优化","预约服务","日历显示效果优化","改变样式",1,"已完成","已评审"]
["小熊",null,"优化","预约服务","只能预约12小时后的服务","只能预约12小时后的服务",1,"已完成","已评审"]
["林泽阳","运营后台","优化",null,"指派后的预约服务需可以在后台取消","指派保洁师后后台也可以取消预约服务，令状态变为客服取消",1,"已完成","已评审"]
["林泽阳","公众号用户端","优化","预约服务","日历显示预约状态（已预约 >预约已满>可预约）",null,3]
["林泽阳","公众号用户端","优化","预约服务","日历显示预约状态为已预约的日期可以点击出现取消该预约的弹窗","日历显示预约状态为已预约的日期可以点击出现取消该预约的弹窗。",3]
["林泽阳","官网","优化","首页","添加一个文章通道","后台可添加文章展示在官网内",0,"已完成","已评审"]
["林泽阳","运营后台","优化",null,"后台帮助用户预约的功能","看原型，后台可主动帮用户预约",0,null,"已评审"]
["林泽阳","公众号用户端","优化","预约服务","预约服务取消的限制","服务12小时前可主动取消，超时联系客服",1,"已完成","已评审"]
["林泽阳","公众号用户端","优化","预约服务","一个订单只能服务一个地址","每个订单的第一次服务的服务地址可填写，从该订单的第二次服务开始，服务地址不可操作（用户取消了第一次预约还是可以修改服务地址）",1,"已完成","已评审"]
["林泽阳","公众号用户端","优化","预约服务","预约服务添加一个留言通道","详看原型",3]
["彭晓莹","公众号用户端","优化","订单设定","添加一个具有推荐人功能的优惠码选项","详看原型",0,"已完成","已评审"]
["海彬","公众号用户端","优化","订单设定","推荐码输入后可立减多少钱","查看",0,"已完成","已评审"]
["林泽阳","运营后台","优化",null,"后台优惠码列表","用户名、手机、产品、价格、推荐渠道、推荐码",0,"已完成","已评审"]
["小熊","运营后台","优化",null,"赠送产品给用户","需要赠送产品给用户的功能，直接在该用户的 “我的服务”页面出现该产品",3]
["林泽阳","公众号用户端","优化",null,"优惠券","优惠券系统",0,"已完成","已评审"]
["林泽阳","运营后台","优化",null,"赠送优惠券功能，优惠券系统","通过后台，或者通过用户的操作",3]
["林泽阳","公众号用户端","优化","预约服务","先选择日期，再选择时间","两个时段分别显示预约已满，两个时段都满了，在日历上的日期才显示已满",1,"已完成","已评审"]
["林泽阳","官网","优化","首页","官网的促销模块","在BANNER和所有产品之间添加一个促销模块",3,"已完成","已评审"]
["林泽阳","公众号用户端","优化","预约服务","用户预约某一天后，取消预约，就再不能预约同一天",null,1,"已完成","已评审"]
["林泽阳","运营后台","优化","产品服务","后台需要可以调整用户产品的服务次数","产品服务的页面，调整用户产品服务次数",0,"已完成"]
["林泽阳","运营后台","优化","产品服务","产品服务的页面表头多添加一行过期时间",null,0,"已完成","已评审"]
["林泽阳","运营后台","优化","产品服务","后台调整用户产品服务的过期时间","看原型",0,"已完成"]
["林泽阳","公众号用户端","优化","预约服务","同一天同个时段的服务预约没有限制"]
["林泽阳","运营后台","优化",null,"订单编号、预约编号、支付编号太短的问题，反应出平台订单量少","变长00+年+月+日+0000",0,"已完成","已评审"]
["林泽阳","公众号用户端","优化","首页","增加一个分类模块","左边体验右边年卡",2]
["林泽阳","公众号用户端","优化","预约服务","当用户在预约服务修改地址后，返回时还是填写之前的地址","页面没有刷新",1,"已完成","已评审"]
["林泽阳","公众号用户端","优化","预约服务","预约服务自动预约","年卡用户，当用户主动预约某一天，弹出弹窗：““是否自动预约每/每两周的星期X”",1]
["林泽阳","官网","优化","首页","官网首页最后面的美观优化",null,null,"已完成"]
["林泽阳","运营后台","优化",null,"运营后台可以取消用户的预约",null,null,"已完成","已评审"]
["李华玲","公众号用户端","优化"," ","添加一个购买商品的功能","产品分类，商品为一类，服务为一类",3]
["林泽阳","公众号用户端","优化","预约服务","新流程的预约按钮不明显",null,1,"已完成","已评审"]
["林泽阳","公众号用户端","优化","预约服务","同个用户购买的不同产品的预约可以共存","即两个产品的预约服务可以是同一时间"]
["林泽阳","运营后台","优化",null,"后台指派保洁师后不能更改"]
["林泽阳","微信模板消息","优化","模板消息","微信的模板消息，当用户进行相关操作时，发送模板消息","购买成功，预约成功，服务已完成",1]
["小熊","运营后台","优化","预约调度","指派保洁师后，页面刷新，没有保留当前筛选的条件，需重新筛选时间",null,1]
["林泽阳","公众号用户端","优化","订单设定","用户输入优惠码确认，成功后toast提示“恭喜获得X元优惠！”",null,1,"已完成","已评审"]
["林泽阳","公众号用户端","优化","我的预约","我的预约的空白页面需要下单跳转提示","看UI图",1]
["林泽阳","官网","优化","首页","首页的整体样式修改","改高端点，看原型，要找人投资了",0,"已完成","已评审"]
["林泽阳","公众号用户端","优化","我的服务","我的服务页面全新版更高级","看UI图",0,"已完成","已评审"]
["林泽阳","公众号用户端","优化","服务卡","用户点击服务卡之后跳转页面（订单详情）",null,0,null,"已评审"]
["林泽阳","公众号用户端","优化","首页","用户端的首页整体样式修改","看UI图",1,null,"已评审"]
["李华玲","公众号用户端","优化","首页","售罄的显示现在外","看UI图，在首页售罄的产品添加一个售罄效果",1]
["林泽阳","运营后台","优化","产品服务","产品服务的筛选功能修改","添加一个产品服务状态筛选（现有的是订单状态）",1]
["林泽阳","运营后台","优化","预约调度","预约调度的筛选功能修改","添加一个用户选择筛选、添加一个上下午筛选、添加一个预约单号筛选",1]
["林泽阳","公众号用户端","优化","购物车","toast提示：下单成功  。改为：正在提交订单",null,1]
["林泽阳",null,"优化",null,"优惠码添加一个用户使用次数的限定",null,1,"已完成","已评审"]
["林泽阳","运营后台","优化","全部","现在表显示大小偏小，需全屏显示的表",null,null,"已完成"]
["林泽阳","公众号用户端","优化","首页","产品的图片需要修改",null,1,"已完成"]
["林泽阳",null,"优化",null,"优惠券添加一个用户使用次数的限定",null,2]
["林泽阳","运营后台","优化","订单总汇","该页面表头添加一个《订单金额》《支付金额》《优惠券/码》","现有的支付金额填写的是订单金额",1]
["林泽阳","公众号用户端","优化","预约服务","预约页面修改","查看原型，添加新的填写内容（我的信息、保洁要求），以及样式修改",3]
[{"$nulls":4},"同一个地址不可下单"]
[{"$nulls":4},"日历页面的按钮"]
["林泽阳","官网","优化","所有产品","所有产品页面有一个关注量的显示（浏览量），去掉",null,1]
["林泽阳","公众号用户端","优化",null,"退款的功能，订单添加两个状态：退款中、已退款","有退款申请提交后，可在后台查看，审核通过退回提交退款申请的金额",1]