{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["22.11.28","22.11.29","22.11.30"],"not_rendered":{"charts":0,"images":5,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"22.11.28","index":0,"n_rows":11,"n_cols":5,"rows_kept":11,"cut":false,"hidden":false,"merged":[]}
[]
[null,"人员","工作内容","遇到问题","需要支持"]
[null,"李忠糠","完成客户管理建模，完成客户管理新增修改接口","无"]
[null,"王辉","爬虫可视化工具Crawlab搭建（已完成），贵州一体机客户协调设备问题（已完成）\n","无"]
[null,"郑子荣","编写下个迭代APP的UI(90%)","无","有几个接口需要后端提供"]
[null,"赖勇兰","需求测试用例编写，进度40%；确认发布前回归测试","无"]
[null,"王颖勋","1.印包管家分包优化，页面路由以及权限的调整等，2.客户管理模块的页面编写","无"]
[null,"张彭杰","1.印包管家需求分析；2.数据建模完成产品库建模","无"]
[null,"胡鹏辉","1.印包管家需求分析；2.修复树根机器数据的字段更新问题","无"]
[null,"李博","产品库列表UI，进度50%，产品创建UI；进度80%；销售单创建UI，进度50%"]
[null,"王振","1.远程办公团队管理沟通；2.印包管家需求评审分析；3.纸通宝工厂版产品验收；","工厂版保活APP代码应该有部分没提交"]

{"sheet":"22.11.29","index":1,"n_rows":11,"n_cols":5,"rows_kept":11,"cut":false,"hidden":false,"merged":[]}
[]
[null,"人员","工作内容","遇到问题","需要支持"]
[null,"李忠糠","1、客户管理模块的联调。2、移动端设备详情编辑调整和联调","无"]
[null,"王辉","1.git服务器挖矿处理，2.Crawlab调试","无"]
[null,"郑子荣","1、完成印包管家UI开发；2、设备编辑和详情与后端进行联调","无"]
[null,"赖勇兰","1、编写测试用例，进度100%；测试客户管理，进度10%"]
[null,"王颖勋","1.客户管理模块的对接，2.工程单模块的初步编写","无"]
[null,"张彭杰","1. 完成销售单、收款单、工程单、采购单、生产单以及外发加工单的数据模型"]
[null,"胡鹏辉","1、需求分析 2、数据模型调整"]
[null,"李博","1：印包管家Web端的销售单和产品库的UI基本上已经完成，整体进度：70%。"]
[null,"王振","1、开发计划跟进和日常项目管理；2、工厂版验收问题修复；"]

{"sheet":"22.11.30","index":2,"n_rows":2,"n_cols":5,"rows_kept":2,"cut":false,"hidden":false,"merged":[[2,1,6,1],[7,1,12,1],[13,1,17,1],[18,1,22,1],[23,1,27,1],[28,1,29,1],[30,1,32,1]]}
[]
[null,"人员","工作内容","遇到问题","需要支持"]