{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["22.11.28)","22.11.29","22.11.30"],"not_rendered":{"charts":0,"images":1,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"22.11.28)","index":0,"n_rows":33,"n_cols":5,"rows_kept":33,"cut":false,"hidden":false,"merged":[[30,1,32,1],[2,1,6,1],[7,1,12,1],[13,1,17,1],[18,1,22,1],[23,1,27,1],[28,1,29,1]]}
[]
[null,"人员","工作内容","遇到问题","需要支持"]
[null,"王振","新版本需求评审（已完成）"]
[null,null,"新版本技术评审（50%）"]
[null,null,"数据建模（5%）",null,"鹏辉彭杰处理中，预计周三，需要琨哥参与确认"]
[null,null,"客户管理（5%）"]
[null,null,"WEB和移动端框架和页面搭建（5%）"]
[null,"曾光福","物流单需求与小程序公众号任务活动需求沟通（完成）"]
[null,null,"物流单需求与小程序公众号任务活动需求沟通排期（未完成）","开发排期时间改期到11月29号完成"]
[null,null,"物流单数据结构设计（完成）"]
[null,null,"商品交付管理，物料单，采购单。开发完成 整体进度（85%）"]
[null,null,"商品交付管理，物料单，采购单交付培训（完成）"]
[null,null,"商品交付管理，物料单，采购单交付 bug修复，\n计划在11月29号回归完成，29号发布完成"]
[null,"臧琨","完成和舒丹的第一轮产品验收工作"]
[null,null,"参加公司周例会"]
[null,null,"和王辉确认爬虫相关事宜，明确了后续工作计划。"]
[null,null,"参与飞鸟新迭代的需求讨论会"]
[null,null,"和颂怀完成物流分开后的UI设计及确认（目前未完成，晚上搞完）"]
[null,"詹浩然","1、完成抖音用粉丝引流维护"]
[null,null,"2、完成废纸报价，排队，分析，日报，成品纸，纸浆等帖子更新维护"]
[null,null,"3、完成企业微信群维护"]
[null,null,"4、完成卧底号挖人工作"]
[null,null,"5、完成纸通宝工厂版远程控制设备开发跟进"]
[null,"张浩然","1、飞鸟快印新一期私域引流相关需求沟通会"]
[null,null,"2、上午参加公司周会"]
[null,null,"3、半天妖第一轮产品验收会议"]
[null,null,"4、刷题小程序开源方案调研，设计私域活跃的基本方案","缺乏完整测试流程，还需要调研内容输出"]
[null,null,"5、其它需求答疑和UI设计工作的跟进"]
[null,"刁颂怀","完成印包后台合作伙伴、产品库、订单管理的设计"]
[null,null,"设计飞鸟多商品查看物流的页面"]
[null,"张山","完成印包管家-当前迭代用户故事编写","无"]
[null,null,"迭代需求评审","无"]
[null,null,"和业务（进华）确认生产录单、跟单事宜","无","进华答应疫情期间在家办公（录单），后续生产管控交邹总负责、刘总（生产总）协同"]

{"sheet":"22.11.29","index":1,"n_rows":31,"n_cols":5,"rows_kept":31,"cut":false,"hidden":false,"merged":[[28,1,29,1],[30,1,32,1],[2,1,6,1],[7,1,12,1],[13,1,17,1],[18,1,22,1],[23,1,27,1]]}
[]
[null,"人员","工作内容","遇到问题","需要支持"]
[null,"王振"]
[]
[]
[]
[]
[null,"曾光福","完成物流单需求与小程序公众号任务活动需求沟通排期，计划在12月07号发布"]
[null,null,"商品交付管理，物料单，采购单整体进度 100%，在11月29号发布完成"]
[null,null,"物流单与小程序，飞鸟公众号需求迭代整体进度 10%"]
[]
[]
[]
[null,"臧琨"]
[]
[]
[]
[]
[null,"詹浩然"]
[]
[]
[]
[]
[null,"张浩然"]
[]
[]
[]
[]
[null,"张山"]
[]
[null,"刁颂怀"]

{"sheet":"22.11.30","index":2,"n_rows":31,"n_cols":5,"rows_kept":31,"cut":false,"hidden":false,"merged":[[30,1,32,1],[2,1,6,1],[7,1,12,1],[13,1,17,1],[18,1,22,1],[23,1,27,1],[28,1,29,1]]}
[]
[null,"人员","工作内容","遇到问题","需要支持"]
[null,"王振"]
[]
[]
[]
[]
[null,"曾光福"]
[]
[]
[]
[]
[]
[null,"臧琨"]
[]
[]
[]
[]
[null,"詹浩然"]
[]
[]
[]
[]
[null,"张浩然"]
[]
[]
[]
[]
[null,"张山"]
[]
[null,"刁颂怀"]